## Sheet1
Milestones
Duration | Tasks
5th - 6th Jan | Design | done
9th Jan | Database creation | done
Front end
10th - 12th Jan | landing page
13th Jan - 18th Jan | course content
courses
19th Jan | login/registration
20th Jan - 24th Jan | payment
Backend
27th Jan | Dashboard
30th Jan - 31st Jan | add,edit,delete,update course names
add,edit,delete,update course content
31st Jan - 1st Feb | view courses
view payments
1st Feb - 2nd Feb | Testing and miscellaneous